## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Risk Register
| Table 1 | Risk Register
Scale
| Table 1 | Scale

## Risk Register
RISK REGISTER TEMPLATE
RISK DESCRIPTION | IMPACT DESCRIPTION | IMPACT LEVEL | PROBABILITY LEVEL | PRIORITY LEVEL | MITIGATION NOTES | OWNER | KEY
Give a brief summary of the risk. | What will happen if the risk is not mitigated or eliminated? | Rate 1 (LOW) to 5 (HIGH) | Rate 1 (LOW) to 5 (HIGH) | (IMPACT X PROBABILITY) Address highest first. | What can be done to lower or eliminate the impact or probability? | Who's responsible? | LEVEL
Accuracy in data collection is crucial | Inaccurate data can lead to inefficient clustering and routing. | 5 | 4 | 20 | Use real-time data collection tools, regularly update the database. | Kush Patel | 1
Performance of algorithms degrade with large datasets | Leads to slower processing times | 5 | 4 | 20 | Optimize algorithms, use parallel processing techniques | Nida Patel | 2
Loss of sensitive data | Damage user trust and lead to legal repercussions | 4 | 4 | 16 | Implement robust access controls and encrypt sensitive data | Kush Patel | 3
Effective handling of dynamic changes | Inefficient routes and delays | 5 | 3 | 15 | Use real-time monitoring systems | Nida Patel | 4
Complex or cluttered UI can overwhelm users | Makes the app difficult to navigate and use. | 5 | 3 | 15 | Implement a minimalist design focusing on essential elements | Yaawar Kapadia | 5
Design Elements can be inconsistent | Confuse users and reduce app's professional appearance | 4 | 3 | 12 | Adhere to a design system or style guide and ensure consistency | Mangalya Shah
UI can be slow or unresponsive | Leads to poor user experience | 4 | 3 | 12 | Optimize use of heavy scripts, libraries and other media assets | Yaawar Kapadia
Integration of various modules may face compatibility issues | System failures or incorrect route generation | 3 | 3 | 9 | Standardized APIs and data formats | Lekhan Patel
User load can be unexpectedly high | Crashes the system, hinders user access and causes downtime | 3 | 2 | 6 | Load Balancing and scalable database architecture | Kush Patel

## Scale
RISK REGISTER SCALE
P R O B A B I L I T Y | 5 | 5 | 10 | 15 | 20 | 25
| 4 | 4 | 8 | 12 | 16 | 20
| 3 | 3 | 6 | 9 | 12 | 15
| 2 | 2 | 4 | 6 | 8 | 10
| 1 | 1 | 2 | 3 | 4 | 5
|  | 1 | 2 | 3 | 4 | 5
I M P A C T